## Submittals
SUBMITTAL LOG
Saddle River Day School - 147 Chestnut Ridge Rd., Saddle River, NJ 07458
DIG Project #22.036 ¦ Contractor: Northern Wolves Air Conditioning
Submittal No. | Spec Section | Description | Manufacturer | Model/Type | Date Submitted | Status | Date Returned | Notes
001 | 230719 | Pipe Insulation - HW and Condensation | Johns Manville | Micro-Lok HP / AP Armaflex | 03/22/2026 | Submitted
002 | 230713 | Duct Wrap Insulation R6 | CertainTeed | Sustainable Insulation | 03/22/2026 | Submitted
003 | 230719 | Refrigeration Pipe Insulation | Armacell | AP Armaflex | 03/22/2026 | Submitted
004 | 237400 | Packaged Rooftop Units w/ Energy Recovery | Carrier | 50XCA Series |  | Pending
005 | 233600 | VAV Terminal Units | Carrier/Titus | Various |  | Pending
006 | 238219 | Hot Water Condensing Boilers | Aerco | Benchmark Series |  | Pending
007 | 232113 | HW Circulation Pumps | Bell & Gossett | e-1510 / e-80 |  | Pending
008 | 233400 | Exhaust Fans | Various | Various |  | Pending
009 | 233400 | Destratification Fans | Various | Various |  | Pending
010 | 238216 | Cabinet Unit Heaters | Various | Various |  | Pending
011 | 238219 | Unit Heaters | Various | Various |  | Pending
012 | 238216 | Hot Water Radiant Ceiling Panels | Various | Various |  | Pending
013 | 238216 | Fin-Tube Radiation | Various | Various |  | Pending
014 | 238126 | Air-Cooled Condensing Units | Various | Various |  | Pending
015 | 232113 | Hydronic Specialties (Exp Tank/Air Sep/Strainer/Chem Feeder) | Various | Various |  | Pending
016 | 233700 | Grilles Registers and Diffusers | Various | Various |  | Pending
017 | 233300 | Fire/Smoke Dampers | Various | Various |  | Pending
018 | 230500 | Needlepoint Bipolar Ionization (NPBI) | GPS | Various |  | Pending
019 | 230713 | Duct Insulation | CertainTeed/Johns Manville | Various |  | Pending
020 | 230523 | Valves | Various | Various |  | Pending
021 | 230529 | Hangers and Supports | Various | Various |  | Pending
022 | 230548 | Vibration and Seismic Controls | Mason Industries | Various |  | Pending
023 | 230913 | BAS/DDC Controls | Various | Various |  | Pending
024 | 230553 | HVAC Identification (Labels/Tags) | Various | Various |  | Pending
025 | 233400 | Lab Hood Exhaust Fans | Various | Various |  | Pending
026 | 233113 | Ductwork - SMACNA Standards | SMACNA | Various |  | Submitted | 03/22/2026 | REVISED - Project-specific per M-002
027 | 232113 | Piping - Hydronic and Condensate (Copper Type L & Sch 40 Steel per M-002) | Various | Various |  | Submitted | 03/22/2026 | REVISED - Project-specific per M-002
028 | 233113 | Acoustical Duct Lining | Johns Manville | Linacoustic RC |  | Submitted | 03/22/2026 | ASTM C1071 Type I fiberglass duct liner
029 | 230529 | Pipe Hangers - FNW Figure 7009Z Clevis (per M-002) | FNW | Figure 7009Z |  | Submitted | 03/22/2026 | REVISED - Project-specific per M-002
030 | 230529 | Anchors | DeWalt | Hangermate+ |  | Submitted | 03/22/2026 | Concrete screw anchors 1/4" to 1/2", ICC-ES
031 | 230548 | Vibration Isolators | Mason/DiversiTech | Type C / ISO-Cube |  | Submitted | 03/22/2026 | Springs, rubber pads, ceiling hung isolators
032 | 230548 | Roof Penetration / RTU Curbs | Various | TC-3 Insulated |  | Submitted | 03/22/2026 | Galv steel insulated curbs, 14" min height
033 | 230548 | Roof Rail Equipment Curbs | Acme Mfg | FEQS/FEQC/FEQRC |  | Submitted | 03/22/2026 | Adjustable equipment support rails
034 | 230529 | Pipe Roof Supports | Various | Adjustable Stand |  | Submitted | 03/22/2026 | Non-penetrating roof pipe supports
035 | 230713 | Fire Wrap Insulation | Various | 1-hr / 2-hr rated |  | Submitted | 03/22/2026 | UL 1978 / UL 2221 fire-rated duct wrap
036 | 233113 | Ductmate Fittings & Accessories | Ductmate | Various |  | Submitted | 03/22/2026 | Flanged connections, access doors, flex conn.
037 | 235216 | SS Vents - Boiler Chimney | Various | AL29-4C SS |  | Submitted | 03/22/2026 | Cat IV double-wall SS vent, UL 1738
038 | 232113 | Condensation Pump | Little Giant | Automatic |  | Submitted | 03/22/2026 | Condensate removal pump with safety switch
039 | 232113 | Condensate Drain - Copper Type L Soldered (per M-002, NOT PVC) | Various | Schedule 40 PVC |  | Submitted | 03/22/2026 | REVISED - Corrected to Copper Type L per M-002